## MSYes
FID | ID | Latitude | Longitude | Initial_Site_ID | Site_ID | Map_ID | Site_ID_Status | Elev_Feet | Elev_meter | Location | State_Province | Country | Landownership | Landowner2 | Landowner3 | Landowner4 | Install_Plan | Notes about Site | Installation_Status | Initial_Recon | Recon_Completed | Site_Constructed | Equipment_Installed | Data_Flow_Started | Station_Certified | Release_Plan | Map_Select
|  | 70.1936 | -161.0812 | A19K | A19K-1 | A19K-1 | Permit Accepted | 125 |  | Kasegaluk | Alaska | USA | BLM |  |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 220 AZ, 5V and Poor Signal @ 90AZ, 3V | New Install | [7 empty] | Yes
|  | 70.4437 | -158.8895 | A20K | A20K-1 | A20K-1 | Permit Accepted | 110 |  | Kolipsun | Alaska | USA | BLM |  |  |  | 2017 Descope | BLM-National Petroleum Reserve, BGAN Good Signal @ 220 AZ, 5 V and Poor Signal @ 90 AZ, 3 V | New Install | [7 empty] | Yes
|  | 71.3221 | -156.6175 | A21K | A21K-6 | A21K | Certified Site | 1893 |  | Barrow | Alaska | USA | USGS | NOAA |  |  | 2014 | Ownership is USGS with an overlapping easment by NOAA (NOAA ARM facility, Radio to fiber optic at DOE/ARM server | New Install |  | 7/2/2013 | 4/24/2014 | 2014-06-02 |  | 2014-07-10 |  | Yes
|  | 71.0033 | -154.9742 | A22K | A22K-2 | A22K-2 | Permit Accepted | 7 |  | Sinclair Lake | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 80 AZ, 4 V | New Install | [7 empty] | Yes
|  | 71.9922 | -125.2617 | A36M | A36M-2 | A36M | Certified Site | 263 |  | Sachs Harbor | Northwest Territory | Canada | First Nation | Parks Canada |  |  | 2014 | At Parks Canada Garage in center of village | New Install |  |  |  |  | 2013-09-03 | 2013-09-10 |  | Yes
|  | 69.3642 | -161.8017 | B18K | B18K-1 | B18K-1 | Permit Accepted | 800 |  | Kokolik | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 220 AZ, 5 V and @ 90 AZ, 3 V | New Install | [7 empty] | Yes
|  | 69.631 | -159.7271 | B19K | B19K-1 | B19K-1 | Permit Accepted | 400 |  | Omik River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 Descope | BLM-National Petroleum Reserve, BGAN Good Signal @ 220 AZ, 5 V and 90 AZ, 3 V | New Install | [7 empty] | Yes
|  | 70.0083 | -157.1594 | B20K | B20K-1 | B20K-1 | Permit Accepted | 240 |  | Meade River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 90 AZ, 10 V and @ 250' 8V | New Install | [7 empty] | Yes
|  | 69.6211 | -154.6127 | B21K | B21K-1 | B21K-1 | Permit Accepted | 315 |  | Koluktah | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 90 AZ, 10 V | New Install | [7 empty] | Yes
|  | 70.34 | -153.4195 | B22K | B22K-1 | B22K-1 | Permit Accepted | 170 |  | Kealok Creek | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 80 AZ, 4 V and 240 AZ | New Install | [7 empty] | Yes
|  | 68.2746 | -165.3435 | C16K | C16K-1 | C16K-1 | Permit Submitted | 350 |  | Maktak | Alaska | USA | Native Patent or IC |  |  |  | 2017 | North Slope Borough, BGAN Good Signal @ 230 AZ, 5 V | New Install | [7 empty] | Yes
|  | 68.4756 | -163.1778 | C17K | C17K-1 | C17K-1 | Permit Accepted | 1600 |  | Kukpowruk River | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2017 | North Shore Borough, BGAN Good Signal @230 AZ, 2 V | New Install | [7 empty] | Yes
|  | 68.6483 | -161.1942 | C18K | C18K-1 | C18K-1 | Permit Accepted | 2800 |  | Utukok River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 120 AZ, 10 V and @ 240 AZ, 8 V | New Install | [7 empty] | Yes
|  | 69.1049 | -159.5873 | C19K | C19K-2 | C19K-2 | Permit Accepted | 2450 |  | Lookout Ridge | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 120 AZ, 10 V and @ 240 AZ, 8 V | New Install | [7 empty] | Yes
|  | 69.4042 | -157.4348 | C20K | C20K-1 | C20K-1 | Permit Accepted | 1130 |  | Discovery Creek | Alaska | USA | BLM | North Slope Borough |  |  | 2017 Descope | BLM-National Petroleum Reserve, BGAN Good Signal @ 90 AZ, 10 V | New Install | [7 empty] | Yes
|  | 69.1565 | -154.7832 | C21K | C21K-1 | C21K-1 | Permit Accepted | 1340 |  | Knifeblade Ridge | Alaska | USA | BLM | North Slope Borough |  |  | 2017 Descope | BLM-National Petroleum Reserve, BGAN Good Signal @ 240 AZ, 10 V | New Install | [7 empty] | Yes
|  | 69.4019 | -151.9587 | C22K | C22K-2 | C22K-2 | Permit Accepted | 450 |  | Umiat | Alaska | USA | Bureau of Land Management | North Slope Borough |  |  | 2016 Descope | BLM-National Petroleum Reserve, BGAN Good Signal @ 110 AZ, 5 V | New Install |  | 7/6/2014 | [5 empty] | Yes
|  | 69.8359 | -150.6125 | C23K | C23K-1 | C23K-1 | Permit Accepted | 600 |  | Itkilik | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 80 AZ, 4 V | New Install |  | 7/4/2014 | [5 empty] | Yes
|  | 69.72 | -148.701 | C24K | C24K-1 | C24K-1 | Permit Accepted | 380 |  | Franklin Bluffs | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 90 AZ, 5 V | New Install |  | 7/5/2014 | [5 empty] | Yes
|  | 69.8981 | -146.5428 | C25K | C25K-1 | C25K-1 | Permit Accepted | 380 |  | Canning River | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 Descope | North Shore Borough, BGAN Good Signal @ 90 AZ, 5 V, Good cell signal out of Pt. Thompson | New Install |  | 7/5/2014 | [5 empty] | Yes
|  | 69.9175 | -144.9122 | C26K | C26K-1 | C26K-1 | Permit Submitted | 380 |  | Camden Bay | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-ANWR, North Slope Borough, BGAN Good Signal @ 90 AZ, 5 V, Possible cell signal out of Pt. Thompson | New Install |  | 7/5/2014 | [5 empty] | Yes
|  | 69.6264 | -143.7114 | C27K | C27K-1 | C27K-1 | Permit Submitted | 1234 |  | Jago River | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System (ANWR), North Slope Borough | New Install |  | 7/5/2014 | [5 empty] | Yes
|  | 69.3476 | -124.0706 | C36M | C36M-2 | C36M | Certified Site | 66 |  | Paulatuk | Northwest Territory | Canada | First Nation |  |  |  | 2014 | At the village recreational center | New Install |  |  | 8/21/2013 | 2013-08-21 | 2013-09-02 | 2013-09-10 |  | Yes
|  | 68.0547 | -162.9049 | D17K | D17K-1 | AK.RDOG | Certified Site-Existing | 170 |  | Eli River | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | At Red Dog Mine, BGAN Good Signal @ 230 AZ, 5 V, Cell coverage likely available with good antenna | Accepted As Is |  | 7/2/2014 |  |  |  | 2015-04-30 |  | Yes
|  | 67.6988 | -163.0831 | D17K | D17K-2 | D17K-2 | Permit Submitted | 630 |  | Noatak | Alaska | USA | State Selected |  |  |  | 2016 |  | New Install |  | 7/2/2014 | [5 empty] | Yes
|  | 68.4946 | -158.115 | D19K | D19K-2 | D19K-2 | Permit Accepted | 2200 |  | Kuna | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 90 AZ, 10 V | New Install |  | 7/2/2014 | [5 empty] | Yes
|  | 68.7135 | -156.6132 | D20K | D20K-2 | D20K-2 | Permit Accepted | 2130 |  | Smith Mtn | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 215 AZ, 10 V | New Install |  | 6/30/2014 | [5 empty] | Yes
|  | 68.8342 | -154.7373 | D21K | D21K-1 | D21K-1 | Permit Accepted | 1560 |  | Heather Creek | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2017 Descope | North Shore Borough, BGAN Good Signal @ 215 AZ, 10 V, Good Signal @ 60 AZ, 3 V | New Install |  | 6/30/2014 | [5 empty] | Yes
|  | 68.8799 | -152.6821 | D22K | D22K-2 | D22K-2 | Permit Accepted | 1800 |  | Ayiyak River | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2017 | North Shore Borough, BGAN Good Signal @ 110 AZ, 5 V | New Install |  | 7/6/2014 | [5 empty] | Yes
|  | 68.9656 | -150.6809 | D23K | D23K-1 | D23K-1 | Permit Accepted | 1300 |  | Nanashuk | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 110 AZ, 5 V | New Install |  | 7/6/2014 | [5 empty] | Yes
|  | 69.1532 | -148.8234 | D24K | D24K-2 | D24K-2 | Permit Accepted | 960 |  | Happy Valley | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 110 AZ, 5 V, Wifi signal active at site from "70 North" camp | New Install |  | 7/6/2014 | [5 empty] | Yes
|  | 69.322 | -146.3752 | D25K | D25K-2 | D25K-2 | Permit Accepted | 2510 |  | Kavik River | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 90 AZ, 5 V | New Install |  | 7/5/2014 | [5 empty] | Yes
|  | 69.243 | -140.9644 | D27M | D27M-1 | D27M-1 | Permit Submitted | 2970 |  | Malcom River | Yukon | Canada | Parks Canada |  |  |  | 2017 | BGAN @140 degrees | New Install |  | 7/28/2014 | [5 empty] | Yes
|  | 69.3286 | -138.7366 | D28M | D28M-5 | D28M-5 | Permit Submitted | 101 |  | Stokes Point | Yukon | Canada | Parks Canada | Military |  |  | 2017 | Stokes Point Early Warning Site BAR-B | New Install | 3/11/2015 | 08/14/2015 | [5 empty] | Yes
|  | 69.5149 | -132.8244 | D31M | D31M-1 | D31M-1 | Recon Target | 82 |  | Tuktoyaktuk | Northwest Territory | Canada | First Nation |  |  |  | 2017 Descope |  | New Install | [7 empty] | Yes
|  | 66.4962 | -163.8422 | E16K | E16K-1 | E16K-1 | Potential-Reconned Primary Site | 44 |  | Cape Espenberg | Alaska | USA | Native Patent or IC |  |  |  | 2017 Descope | Kotzebue (Village of), National Park Service-Bering Land Bridge, BGAN signal fair 230 deg. Az. 3 deg V | New Install |  | 6/7/2014 | [5 empty] | Yes
|  | 67.0819 | -161.826 | E17K | E17K-1 | E17K-1 | Permit Submitted | 730 |  | Kotzebue | Alaska | USA | BLM |  |  |  | 2016 | BGAN good signal 100 Az, 08 V | New Install |  | 6/8/2014 | [5 empty] | Yes
|  | 67.4208 | -160.598 | E18K | E18K-1 | E18K-1 | Permit Accepted | 980 |  | Omar River | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal excellent @ 235 deg. Az. 15 deg V | New Install |  | 6/9/2014 | [5 empty] | Yes
|  | 67.4689 | -157.2255 | E19K | E19K-2 | E19K-2 | Permit Accepted | 1740 |  | Redstone River | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN signal good @ 240 deg. Az. 8 deg V | New Install |  | 6/9/2014 | [5 empty] | Yes
|  | 68.2575 | -156.1885 | E20K | E20K-5 | E20K-5 | Permit Submitted | 2850 |  | Nigu River | Alaska | USA | Bureau of Land Management | North Slope Borough |  |  | 2017 |  | New Install |  | 09/08/2015 | [5 empty] | Yes
|  | 68.4414 | -153.972 | E21K | E21K-1 | E21K-1 | Permit Submitted | 2120 |  | Killik River | Alaska | USA | Native Patent or IC |  |  |  | 2017 | North Slope Borough, BGAN Good Signal @ 240 AZ, 10 V | New Install |  | 6/30/2014 | [5 empty] | Yes
|  | 68.1343 | -151.8132 | E22K | E22K-1 | E22K-1 | Permit Submitted | 2250 |  | Anaktuvuk | Alaska | USA | Native Patent or IC |  |  |  | 2016 | National Park Service-Gates of the Arctic, North Slope Borough | New Install |  | 6/30/2014 | [5 empty] | Yes
|  | 68.6408 | -149.5724 | E23K | E23K | TOLK | Certified Site | 2434 |  | Toolik Lake Research Station | Alaska | USA | BLM |  |  |  | 2014 | UAF Arctic Biology LTER Research Station | New Install | 10/4/2010 |  |  | 2013-08-13 |  | 2013-08-19 |  | Yes
|  | 68.0584 | -149.6164 | E23K | E23K-3 | E23K-3 | Permit Accepted | 3153 |  | James Dalton Mtn | Alaska | USA | BLM | North Slope Borough |  |  | 2016 | Chandalar Shelf Camp, Airport | New Install |  | 06/13/2014 | [5 empty] | Yes
|  | 68.0748 | -148.4868 | E24K | E24K-1 | E24K-1 | Permit Accepted | 2790 |  | Your Creek | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | DNR, BGAN signal good @ 110 deg. Az. 5 deg V | New Install |  | 6/11/2014 | [5 empty] | Yes
|  | 68.1207 | -145.5679 | E25K | E25K-1 | E25K-1-PB.AB46 | Potential-Existing Other Station | 2054 |  | Arctic Village | Alaska | USA | Native Patent or IC |  |  |  | 2016 | FWS-National Refuge System | New Install | [7 empty] | Yes
|  | 68.3454 | -144.4492 | E26K | E26K-1 | E26K-1 | Permit Submitted | 2100 |  | Arctice Village | Alaska | USA | FWS |  |  |  | 2016 Descope | FWS-National Refuge System-ANWR | New Install |  | 6/13/2014 | [5 empty] | Yes
|  | 68.1862 | -141.5958 | E27K | E27K-1 | E27K-1 | Permit Submitted | 2100 |  | Bilwaddy Creek | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-ANWR | New Install |  | 6/13/2014 | [5 empty] | Yes
|  | 68.6043 | -139.5351 | E28M | E28M-4 | E28M-4 | Permit Submitted | 1499 |  | Babbage River | Yukon | Canada | Crown Land |  |  |  | 2017 |  | New Install |  | 08/14/2015 | [5 empty] | Yes
|  | 68.3888 | -137.8969 | E29M | E29M-2 | E29M-2 | Permit Submitted | 1030 |  | Blow River | Yukon | Canada | Crown Land |  |  |  | 2017 | BGAN @ 130 degrees | New Install |  | 7/27/2014 | [5 empty] | Yes
|  | 68.4945 | -135.8437 | E30M | E30M-2 | E30M-2 | Potential-Reconned Primary Site | 600 |  | Cache Creek | Northwest Territory | Canada | Inuvialuit Settlement Lands |  |  |  | 2017 Descope | Inuvialuit Settlement Lands | New Install |  | 7/28/2014 | [5 empty] | Yes
|  | 68.31 | -133.53 | E31M | E31M-1 | CN.INK | Certified Site-Existing | 175 |  | Rampart House | Northwest Territory | Canada | Existing |  |  |  | 2015 Existing | Canadian National Network site | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 65.5606 | -167.924 | F13K | F13K-1 | AK.TNA | Certified Site-Upgraded | 257 |  | Diomede | Alaska | USA | Military |  |  |  | 2015 Existing | MIL-Dept of Air Force | Accepted As Is |  |  |  | 2014-10-06 |  | 2014-10-13 |  | Yes
|  | 65.4742 | -166.3285 | F14K | F14K-2 | F14K-2 | Permit Accepted | 870 |  | Brevig | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN signal fair 240 deg. Az. 5 deg V | New Install |  | 6/7/2014 | [5 empty] | Yes
|  | 65.7077 | -164.6481 | F15K | F15K-1 | F15K-1 | Permit Accepted | 1250 |  | Taylor | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 6/7/2014 | [5 empty] | Yes
|  | 65.868 | -162.8081 | F16K | F16K-2 | F16K-2 | Permit Accepted | 560 |  | Kugruk | Alaska | USA | State Patent or TA |  |  |  | 2017 Descope | DNR, BGAN signal excellent @ 230 deg. Az. 3 deg V | New Install |  | 6/8/2014 | [5 empty] | Yes
|  | 66.442 | -161.2502 | F17K | F17K-1 | F17K-1 | Permit Submitted | 162 |  | Baldwin Peninsula | Alaska | USA | BLM |  |  |  | 2016 | BGAN signal excellent @ 230 deg. Az. 13 deg V | New Install |  | 6/8/2014 | [5 empty] | Yes
|  | 66.6001 | -159.6515 | F18K | F18K-1 | F18K-1 | Potential-Reconned Primary Site | 55 |  | Selawik | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Selawik (Village of), FWS-National Refuge System, BGAN signal excellent @ 230 deg. Az. 10 deg. V | New Install |  | 6/8/2014 | [5 empty] | Yes
|  | 66.885 | -157.1538 | F19K | F19K-1 | F19K-1 | Potential-Reconned Primary Site | 200 |  | Shungnak | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Shungnak (Village of), Private ("Native Townsite " ~Native Patent/Village), ADOT | New Install |  | 6/9/2014 | [5 empty] | Yes
|  | 67.0486 | -155.7251 | F20K | F20K-2 | F20K-2 | Permit Accepted | 440 |  | Mauneluk | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN signal good @ 110 deg. Az. 6 deg. V | New Install |  | 6/10/2014 | [5 empty] | Yes
|  | 67.2215 | -153.4803 | F21K | F21K-2 | F21K-2 | Permit Accepted | 1950 |  | Alatna River | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal good @ 115 deg. Az. 8 deg. V | New Install |  | 6/10/2014 | [5 empty] | Yes
|  | 67.5076 | -152.1789 | F22K | F22K-2 | F22K-2 | Permit Accepted | 1785 |  | John River | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal weak @115 deg. Az. 8 deg V | New Install |  | 6/10/2014 | [5 empty] | Yes
|  | 67.2274 | -150.2013 | F23K | F23K-2 | AK.COLD | Certified Site-Upgraded | 1176 |  | Coldfoot Broadband | Alaska | USA | BLM |  |  |  | 2014 Existing |  | Station Upgrade |  |  | 6/12/2014 | 2014-07-02 |  | 2014-07-29 |  | Yes
|  | 67.5189 | -147.8871 | F24K | F24K-1 | F24K-1 | Permit Accepted | 2400 |  | Chandalar | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal good @ 110 deg. Az. 5 deg. V | New Install |  | 6/11/2014 | [5 empty] | Yes
|  | 67.7028 | -145.7884 | F25K | F25K-3 | F25K-3 | Potential-Reconned Primary Site | 2500 |  | Arctic Village | Alaska | USA | Native Patent or IC |  |  |  | 2016 | BGAN Signal Good 6 deg. Az. 5 deg. V. |  |  | 6/13/2014 | [5 empty] | Yes
|  | 67.6962 | -144.136 | F26K | F26K-2 | F26K-2 | Permit Submitted | 2100 |  | Sheenjek | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-ANWR, BGAN not verified, but should be good signal from east. | New Install |  | 6/13/2014 | [5 empty] | Yes
|  | 67.7518 | -142.0528 | F27K | F27K-1 | F27K-1 | Permit Submitted | 1900 |  | Strangle Woman Creek | Alaska | USA | FWS |  |  |  | 2016 Descope | FWS-National Refuge System-ANWR | New Install |  | 6/13/2014 | [5 empty] | Yes
|  | 67.5668 | -139.8486 | F28M | F28M-2 | F28M-2 | Permit Submitted | 817 |  | Old Crow | Yukon | Canada | Crown Land |  |  |  | 2017 | Environment Canada | New Install |  | 7/28/2014 | [5 empty] | Yes
|  | 67.6991 | -137.6331 | F29M | F29M-2 | F29M-2 | Permit Submitted | 2000 |  | Rat Indian Creek | Yukon | Canada | Crown Land |  |  |  | 2017 Descope | North Yukon Land Management Area - Driftwood River Salmon Cache IMA Zone II, BGAN @ 135 degrees | New Install |  | 7/27/2014 | [5 empty] | Yes
|  | 67.6106 | -135.7866 | F30M | F30M-2 | F30M-2 | Potential-Reconned Primary Site | 1340 |  | Barrier River | Northwest Territory | Canada | Crown Land |  |  |  | 2017 Descope | Crown, BGAN @ 140 degrees | New Install |  | 7/28/2014 | [5 empty] | Yes
|  | 67.441 | -133.7419 | F31M | F31M-T1 | F31M-T1 | Permit Accepted | 145 |  | Tsiigehtchic | Northwest Territory | Canada | Tsiigehtchic Charter Community |  |  |  | 2016 | DSL available through NWTel, Option to use visitor center connection-TBD, Cabling: Use same cable port as power (to be installed) | New Install |  | 8/14/2014 | [5 empty] | Yes
|  | 63.7767 | -171.7008 | G09K | G09K-1 | AK.GAMB | Certified Site-Upgraded | 10 |  | Gambell | Alaska | USA | Native Patent or IC |  |  |  | 2015 Existing | FWS-National Refuge System | Station Upgrade | [5 empty] | 2015-04-30 |  | Yes
|  | 63.6569 | -170.5674 | G10K | G10K-1 | G10K-1-PB.AB04 | Potential-Existing Other Station | 357 |  | Savoonga | Alaska | USA | Native Patent or IC |  |  |  | 2017 Descope | FWS-National Refuge System | New Install | [7 empty] | Yes
|  | 64.976 | -168.066 | G13K | G13K | G13K | Initial Site | 1 |  | King Island | Alaska | USA | Native Patent or IC |  |  |  | 2017 Descope | King Island (Village), FWS-National Refuge System | New Install | [7 empty] | Yes
|  | 64.5653 | -165.3706 | G14K | G14K-1 | AK.ANM | Certified Site-Existing | 358 |  | Anvil Mountain | Alaska | USA | Military |  |  |  | 2015 Existing | National Patent or IC, Native Select, Private, MIL-Dept of Air Force | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 64.9941 | -164.0386 | G15K | G15K-3 | G15K-3 | Permit Accepted | 850 |  | Niukluk | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN Signal Good 210 deg. 10 deg. V | New Install |  | 6/6/2014 | [5 empty] | Yes
|  | 65.3937 | -162.3549 | G16K | G16K-1 | G16K-1 | Permit Accepted | 550 |  | Koyuk | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN Signal Good 110 deg. Az. 10 deg. | New Install |  | 6/6/2014 | [5 empty] | Yes
|  | 65.6756 | -160.6183 | G17K | G17K-3 | G17K-3 | Permit Submitted | 155 |  | Buckland River | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/22/2014 | [5 empty] | Yes
|  | 65.8949 | -158.6539 | G18K | G18K-2 | G18K-2 | Permit Submitted | 1500 |  | Tagagawik | Alaska | USA | BLM |  |  |  | 2017 | BGAN signal good @ 110 deg. Az. 13 deg. V | New Install |  | 6/6/2014 | [5 empty] | Yes
|  | 66.1434 | -157.0872 | G19K | G19K-4 | G19K-4 | Permit Accepted | 1300 |  | Purcell Mt. | Alaska | USA | State Selected |  |  |  | 2017 | BGAN signal good @ 110 deg. Az. 13 deg. V | New Install |  | 6/6/2014 | [5 empty] | Yes
|  | 66.1586 | -155.0716 | G20K | G20K-1 | G20K-1 | Permit Accepted | 1700 |  | Babantaltilin Hills | Alaska | USA | BLM |  |  |  | 2016 Descope | BGAN signal good @ 110 deg. Az. 13 deg. V | New Install |  | 6/6/2014 | [5 empty] | Yes
|  | 66.5155 | -153.5057 | G21K | G21K-3 | G21K-3 | Permit Accepted | 1450 |  | Allakaket | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal good @ 120 deg. Az. 10 deg. V | New Install |  | 6/11/2014 | [5 empty] | Yes
|  | 66.918 | -151.5191 | G22K | G22K-1 | G22K-1 | Potential-Reconned Primary Site | 635 |  | Bettles | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Evansville (Village of), Cell service available, BGAN signal good @ 110 deg. Az. 5 deg. V | New Install |  | 6/12/2014 | [5 empty] | Yes
|  | 66.71 | -150.0259 | G23K | G23K-1 | G23K-1 | Permit Accepted | 2300 |  | Bonanza Creek | Alaska | USA | State Selected |  |  |  | 2016 | BGAN signal good @ 110 deg. Az. 10 deg. V | New Install |  | 6/11/2014 | [5 empty] | Yes
|  | 66.701 | -147.4746 | G24K | G24K-2 | G24K-2 | Permit Submitted | 1692 |  | Beaver | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-Yukon Flats, BGAN signal good @ 100 deg. Az. 10 deg. V, BGAN signal good @ 230 deg. Az. 10 deg. V | New Install |  | 6/12/2014 | [5 empty] | Yes
|  | 66.7653 | -146.1014 | G25K | G25K-2 | G25K-2 | Permit Submitted | 450 |  | Bearman Lake | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-Yukon Flats, BGAN signal good @ 100 deg. Az. 10 deg. V, BGAN signal good @ 230 deg. Az. 10 deg. V | New Install |  | 6/12/2014 | [5 empty] | Yes
|  | 66.9492 | -143.7867 | G26K | G26K-2 | G26K-2 | Permit Submitted | 600 |  | Shyman | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-Yukon Flats, BGAN signal good @ 100 Az., V 10 deg. | New Install |  | 6/14/2014 | [5 empty] | Yes
|  | 66.8089 | -141.6546 | G27K | G27K-3 | G27K-3 | Permit Accepted | 2250 |  | Doyon #3 | Alaska | USA | Native Patent or IC |  |  |  | 2016 | FWS-National Refuge System-ANWR, BGAN signal good @ 110deg. Az. 10 deg | New Install |  | 6/14/2014 | [5 empty] | Yes
|  | 67.1235 | -139.7307 | G28M | G28M-1 | G28M-1 | Permit Submitted | 2140 |  | Ahvee Mtn | Yukon | Canada | Crown Land |  |  |  | 2017 Descope | North Yukon Land Management Area - Ahvee & Sharp Mtns IMA Zone III, BGAN @ 135 degrees | New Install |  | 7/27/2014 | [5 empty] | Yes
|  | 66.9116 | -138.0224 | G29M | G29M-1 | G29M-1 | Permit Submitted | 1890 |  | Pine Creek | Yukon | Canada | Crown Land |  |  |  | 2017 | North Yukon Land Management Area - Johnson Creek IMA Zone IV, BGAN @ 140 degrees | New Install |  | 7/27/2014 | [5 empty] | Yes
|  | 66.981 | -136.2213 | G30M | G30M-T2 | G30M-T2 | Permit Submitted | 2414 |  | Yukon-NWT Border Region | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2016 | VSAT: Horizon SE 6 degrees | New Install |  | 8/9/2014 | [5 empty] | Yes
|  | 66.9227 | -134.2708 | G31M | G31M-1 | G31M-1 | Permit Submitted | 200 |  | Satah River | Yukon | Canada | Crown Land |  |  |  | 2017 Descope | Peel River Watershed Land Management Area - Jackfish Lakes IMA Zone II | New Install |  | 7/29/2014 | [5 empty] | Yes
|  | 64.6172 | -162.2615 | H16K | H16K-1 | H16K-1-PB.AC31 | Potential-Existing Other Station | 44 |  | Elim | Alaska | USA | Native Patent or IC |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 64.9371 | -159.9126 | H17K | H17K-1 | H17K-1 | Permit Submitted | 1300 |  | Ungalik River | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/22/2014 | [5 empty] | Yes
|  | 65.1526 | -158.3635 | H18K | H18K-1 | H18K-1 | Permit Submitted | 1640 |  | Honhonsa River | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/21/2014 | [5 empty] | Yes
|  | 65.5276 | -156.4496 | H19K | H19K-2 | H19K-2 | Permit Accepted | 390 |  | Roundabout Mt | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Native Patent or IC, FWS-National Refuge System-Koyukuk | New Install |  | 5/21/2014 | [5 empty] | Yes
|  | 65.4923 | -154.8809 | H20K | H20K-1 | H20K-1 | Permit Accepted | 1648 |  | Anotleneega Mt. | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/21/2014 | [5 empty] | Yes
|  | 65.6571 | -152.805 | H21K | H21K-4a | H21K | Certified Site | 1707 |  | Melozitna River | Alaska | USA | BLM |  |  |  | 2015 |  | New Install |  |  | 5/30/2015 | 2015-05-31 | 2015-06-04 | 2015-06-04 |  | Yes
|  | 65.8937 | -151.3774 | H22K | H22K-3-1 | H22K-3-1 | Permit Accepted | 1824 |  | Ishtalitna Creek | Alaska | USA | BLM |  |  |  | 2016 |  | New Install |  | 06/22/2013 | [5 empty] | Yes
|  | 65.8251 | -149.5432 | H23K | H23K-5 | H23K | Certified Site | 2024 |  | Repeater Hill | Alaska | USA | State Patent or TA |  |  |  | 2015 | DNR | New Install | 05/31/2014 | 06/15/2014 | 5/20/2015 | 2015-05-21 | 2015-05-21 | 2015-05-29 |  | Yes
|  | 65.8371 | -147.8781 | H24K | H24K-3a | H24K | Certified Site | 2672 |  | Nodoor Dome | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 5/26/2015 | 2015-05-27 | 2015-05-28 | 2015-05-29 |  | Yes
|  | 66.267 | -145.8196 | H25K | H25K-1-2 | H25K-1-2 | Potential-Reconned Primary Site | 440 |  | Birch Creek Village | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Birch Creek (Village of), Native Select, Native Patent or IC, FWS-Yukon Flats, Private | New Install | [7 empty] | Yes
|  | 65.8265 | -144.074 | H26K | H26K-1 | H26K-1 | Potential-Reconned Primary Site | 600 |  | Circle Airport | Alaska | USA | Native Lands |  |  |  | 2016 Descope | Circle Village | New Install | [7 empty] | Yes
|  | 66.2306 | -141.5265 | H27K | H27K-9 | H27K-9 | Permit Accepted | 2526 |  | Steamboat Mountain | Alaska | USA | State Selected |  |  |  | 2016 |  | New Install |  | 06/25/2013 | [5 empty] | Yes
|  | 66.1855 | -139.705 | H28M | H28M-1 | H28M-1 | Potential-Reconned Primary Site | 2770 |  | Fishing Branch River | Yukon | Canada | Parks Canada |  |  |  | 2017 Descope | Peel River Watershed Land Management Area - Fishing Branch Protected Area (Fishing Branch Park) | New Install |  | 7/25/2014 | [5 empty] | Yes
|  | 66.2192 | -138.3689 | H29M | H29M-1 | H29M-1 | Permit Submitted | 1570 |  | Whitestone | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Whitestone River IMA Zone III | New Install |  | 7/25/2014 | [5 empty] | Yes
|  | 66.3701 | -136.7191 | H30M | H30M | EPYK | Certified Site | 717 |  | Eagle Plains | Yukon | Canada | Existing |  |  |  | 2014 |  | New Install |  |  |  | 2012-10-10 |  | 2012-10-15 |  | Yes
|  | 65.8053 | -134.3427 | H31M | H31M-2 | H31M-2 | Permit Submitted | 2100 |  | Noisy Creek | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Snake River Restricted Use Wilderness Area, BGAN @ 140 degrees | New Install |  | 7/26/2014 | [5 empty] | Yes
|  | 63.8864 | -160.6947 | I17K | I17K-1 | I17K-1-PB.AB17 | Potential-Existing Other Station | 117 |  | Kaltag | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Native Select | New Install | [7 empty] | Yes
|  | 64.508 | -157.8088 | I18K | I18K-2 | I18K-2 | Permit Accepted | 144 |  | Gorton Creek | Alaska | USA | Native Patent or IC |  |  |  | 2017 Descope | FWS-National Refuge System-Innoko | New Install |  | 5/22/2014 | [5 empty] | Yes
|  | 64.7461 | -156.8792 | I19K | I19K-2 | I19K-2-AK.GCSA | Certified Site-Existing | 130 |  | Ruby | Alaska | USA | Native Patent or IC |  |  |  | 2015 Existing | AEC will rebuild using existing borehole-no TA requirement | Accepted As Is |  |  | 07/01/2015 | 2015-07-01 | 2015-07-02 | 2015-07-29 |  | Yes
|  | 64.7964 | -154.4779 | I20K | I20K-2 | I20K-2 | Permit Submitted | 225 |  | Grass Lake to W | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Nowitna |  |  | 5/21/2014 | [5 empty] | Yes
|  | 65.18 | -151.9822 | I21K | I21K-3 | I21K | Certified Site | 844 |  | Tanana | Alaska | USA | Native Patent or IC |  |  |  | 2015 | Tanana Tribal Council | New Install |  | 5/15/2015 | 5/30/2015 | 2015-05-31 | 2015-06-01 | 2015-06-16 |  | Yes
|  | 65.0308 | -150.7392 | I22K | I22K-1 | AK.MLY | Certified Site-Upgraded | 2677 |  | Manley Hot Springs | Alaska | USA | Native Patent or IC |  |  |  | 2014 Existing | Manley Hot Springs (Village of), Private | Station Upgrade |  |  | 9/10/2014 |  | 2014-09-12 | 2014-10-03 |  | Yes
|  | 65.1479 | -149.3603 | I23K | I23K-4 | I23K | Certified Site | 489.5 |  | Minto, Yukon-Koyukuk | Alaska | USA | Native Patent or IC |  |  |  | 2014 | Minto (Village) | New Install |  |  | 9/12/2014 | 2014-09-13 |  | 2014-10-20 |  | Yes
|  | 64.8736 | -147.8616 | I24K | I24K | IU.COLA | Certified Site-Existing | 650 |  | College Outpost | Alaska | USA | Existing |  |  |  | 2014 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 65.1171 | -147.4335 | I24K | I24K-2 | POKR | Certified Site | 501 |  | Poker Flat Research Range | Alaska | USA | State Patent or TA |  |  |  | 2014 |  | New Install |  |  |  | 2012-10-02 |  | 2012-10-17 |  | Yes
|  | 65.52 | -145.52 | I25K | I25K-1 | I25K-1-AK.PPD | Planned Upgrade-Existing | 4278 |  | Central | Alaska | USA | State Patent or TA |  |  |  | 2016 Existing |  | Station Upgrade | [7 empty] | Yes
|  | 65.3064 | -143.1541 | I26K | I26K-1-2 | I26K | Equipment Installed | 1108 |  | Coal Creek Mining Camp | Alaska | USA | NPS |  |  |  | 2015 | Yukon-Charley River, Description: S25 T6N R22E, Fairbanks Meridian | New Station |  |  | 09/12/2015 | 2015-09-12 |  |  |  | Yes
|  | 65.604 | -141.616 | I27K | I27K-5 | I27K-5 | Permit Accepted | 2772 |  | Kandik River | Alaska | USA | BLM |  |  |  | 2016 |  | New Install |  | 06/25/2013 | [5 empty] | Yes
|  | 65.4482 | -139.9353 | I28M | I28M-2 | I28M-2 | Permit Submitted | 3875 |  | Miner River | Yukon | Canada | Crown Land |  |  |  | 2017 | Crown, BGAN @ 140 degrees | New Install |  | 7/24/2014 | [5 empty] | Yes
|  | 65.3609 | -138.3063 | I29M | I29M-T1 | I29M | Certified Site | 1974 |  | Ogilvie River Highway Camp, Dempster Highway | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2015 |  | New Install |  | 8/15/2014 | 10/20/2015 | 2015-10-20 | 2015-10-20 | 2015-10-20 |  | Yes
|  | 65.2225 | -136.3766 | I30M | I30M-1 | I30M-1 | Permit Submitted | 4570 |  | Mt. Dempster | Yukon | Canada | Crown Land |  |  |  | 2017 Descope | Peel River Watershed Land Management Area - Hart River Restricted Use Wilderness, BGAN @ 140 degrees | New Install |  | 7/25/2014 | [5 empty] | Yes
|  | 62.7492 | -163.5539 | J14K | J14K-1 | J14K-1 | Permit Submitted | 120 |  | Nanvaranak Lake | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | [5 empty] | Yes
|  | 63.1497 | -162.1652 | J15K | J15K-1 | J15K-1 | Potential-Reconned Primary Site | 830 |  | Kogak River | Alaska | USA | Native Patent or IC |  |  |  | 2017 Descope | Stebbins (Village), FWS-National Refuge System-Yukon Delta | New Install |  | 5/23/2014 | [5 empty] | Yes
|  | 63.2843 | -160.6021 | J16K | J16K-2 | J16K-2 | Permit Submitted | 1050 |  | Anvik River | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/22/2014 | [5 empty] | Yes
|  | 63.3966 | -159.0777 | J17K | J17K-1 | J17K-1 | Permit Submitted | 1020 |  | VABM Dome | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Innoko | New Install |  | 5/22/2014 | [5 empty] | Yes
|  | 63.4649 | -156.7157 | J18K | J18K-4 | J18K-4 | Permit Accepted | 1644 |  | Finland Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 63.9943 | -155.6215 | J19K | J19K-2 | J19K-2 | Permit Accepted | 1278 |  | Cache Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 64.1767 | -154.1467 | J20K | J20K-2 | J20K | Certified Site | 994 |  | Nowitna River | Alaska | USA | BLM |  |  |  | 2015 |  | New Install |  | 09/22/2013 | 06/30/2015 | 2015-07-01 | 2015-07-02 |  |  | Yes
|  | 63.8827 | -152.3152 | J21K | J21K-1 | AK.CHUM | Certified Site-Upgraded | 927 |  | Lake Minchumina | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing |  | Station Upgrade |  |  | 07/03/2015 | 2015-07-03 |  |  |  | Yes
|  | 64.1002 | -150.9848 | J22K | J22K-1 | AK.BPAW | Certified Site-Existing | 1910 |  | Bear Paw Mountain | Alaska | USA | State Selected |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 64.5928 | -149.0694 | J23K | J23K-1 | AK.NEA2 | Certified Site-Upgraded | 1476 |  | Nenana | Alaska | USA | Native Patent or IC |  |  |  | 2014 Existing | State Patent or TA, State Microwave | Station Upgrade |  |  | 6/8/2014 | 2014-07-09 |  | 2014-07-29 |  | Yes
|  | 64.4057 | -146.9407 | J24K | J24K | AK.HDA | Certified Site-Upgraded | 437 |  | Harding Lake | Alaska | USA | State Patent or TA |  |  |  | 2014 Existing | State Select, Private, State Microwave | Station Upgrade |  |  |  | 2012-10-01 |  | 2012-10-05 |  | Yes
|  | 64.613 | -145.3697 | J25K | J25K-6-1 | J25K | Certified Site | 949 |  | Salcha River | Alaska | USA | State Patent or TA |  |  |  | 2015 | This site is approximately 0.4 miles from the orginally propsed location 64.61377, -145.38504, but still within the DNR permit boundaries | New Install |  |  | 08/24/2015 | 2015-08-25 | 2015-08-25 | 2015-08-25 |  | Yes
|  | 64.501 | -143.5636 | J26L | J26L-5 | J26L | Certified Site | 3753 |  | Joseph Creek | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  | 06/26/2013 | 09/10/2015 | 2015-09-11 | 2015-09-11 | 2015-09-11 |  | Yes
|  | 64.7774 | -141.158 | J27K | J27K-1 | US.EGAK | Certified Site-Existing | 892 |  | Eagle | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 64.7749 | -139.9102 | J28M | J28M-2 | J28M-2 | Permit Submitted | 4180 |  | Coal Creek | Yukon | Canada | Crown Land |  |  |  | 2017 Descope | Crown, DESCOPE, made primary after primary site J23M-1 was rejected, BGAN @ 135 degrees |  |  | 7/24/2014 | [5 empty] | Yes
|  | 64.453 | -138.2158 | J29M | J29M-T3 | J29M | Certified Site | 3167 |  | Klondike Camp | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2015 |  | New Install |  | 8/7/2014 | 10/21/2015 | 2014-10-21 | 2015-10-21 | 2015-10-21 |  | Yes
|  | 64.5753 | -136.3305 | J30M | J30M-1 | J30M-1 | Permit Submitted | 4670 |  | Taiga Valley | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Hart River Restricted Use Wilderness Area, BGAN @ 140 degrees | New Install |  | 7/25/2014 | [5 empty] | Yes
|  | 60.421 | -172.689 | K07K | K07K | K07K | Initial Site | 1 |  | Mekoryuk | Alaska | USA | FWS |  |  |  | 2017 Descope |  | New Install | [7 empty] | Yes
|  | 61.9331 | -164.6555 | K13K | K13K-1 | K13K-1 | Potential-Reconned Primary Site | 670 |  | Ulokat Hills | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Hooper Bay (Village), FWS-National Refuge System-Yukon Delta | New Install |  | 5/25/2014 | [5 empty] | Yes
|  | 62.171 | -163.1301 | K14K | K14K-2 | K14K-2 | Potential-Reconned Primary Site | 488 |  | Andreafsky Hills | Alaska | USA | Native Patent or IC |  |  |  | 2017 Descope | St. Mary's (Village), FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | [5 empty] | Yes
|  | 62.2937 | -161.5309 | K15K | K15K-1 | K15K-1 | Permit Submitted | 1050 |  | Rolling Hills | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/23/2014 | [5 empty] | Yes
|  | 62.395 | -160.1731 | K16K | K16K-1 | K16K-1 | Permit Submitted | 850 |  | Long Mountains | Alaska | USA | BLM |  |  |  | 2017 Descope |  | New Install |  | 5/23/2014 | [5 empty] | Yes
|  | 62.7161 | -158.3011 | K17K | K17K-2 | K17K-2 | Permit Accepted | 1094 |  | Little Yetna River | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 62.9952 | -157.3351 | K18K | K18K-6 | K18K-6 | Permit Accepted | 1312 |  | Beaver Mtns | Alaska | USA | State Patent or TA |  |  |  | 2017 Descope |  | New Install | [7 empty] | Yes
|  | 62.93 | -156.01 | K19K | K19K-2 | AT.TTA | Planned Upgrade-Existing | 2277 |  | Tatalina | Alaska | USA | Military |  |  |  | 2017 Existing | State Select, MIL-Dept of Air Force. Tsunami Warning Center site. | Station Upgrade | [7 empty] | Yes
|  | 63.3569 | -154.07 | K20K | K20K-4b | K20K | Certified Site | 1748 |  | Telida | Alaska | USA | State Patent or TA |  |  |  | 2015 | DNR | New Install |  |  | 06/30/2015 | 2015-06-30 | 2015-07-02 |  |  | Yes
|  | 63.4193 | -152.0682 | K21K | K21K-2 | AK.CAST | Planned Upgrade-Existing | 1788 |  | Castle Rocks | Alaska | USA | National Park Service |  |  |  | 2016 Existing |  | Station Upgrade | [7 empty] | Yes
|  | 63.451 | -150.2872 | K22K | K22K-2 | AK.TRF | Planned Upgrade-Existing | 5529 |  | Thorofare Mountain | Alaska | USA | National Park Service |  |  |  | 2016 Existing | NPS-Wilderness Desig | Station Upgrade | [7 empty] | Yes
|  | 63.7323 | -148.9349 | K23K | K23K-1 | AK.MCK | Certified Site-Upgraded | 5315 |  | McKinley Park | Alaska | USA | National Park Service |  |  |  | 2014 Existing | Private | Station Upgrade |  |  |  | 2014-09-26 |  | 2014-10-03 |  | Yes
|  | 63.8036 | -145.7784 | K24K | K24K-3 | K24K-3 | Permit Submitted | 2345.8 |  | Alascom/Military Telecommunications Site | Alaska | USA | Military | Bureau of Land Management |  |  | 2016 | Dept. of Defense-Lease Alaskacom/AT&T through BLM | New Install |  | 4/17/2015 | [5 empty] | Yes
|  | 63.7407 | -144.8417 | K25K | K25K-1 | AK.RIDG | Certified Site-Upgraded | 2612 |  | Independent Ridge | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing |  | Station Upgrade |  |  | 07/07/2015 | 2015-07-08 | 2007-01-07 | 2015-02-20 |  | Yes
|  | 63.9769 | -143.9859 | K26K | K26K-1 | AK.SCRK | Certified Site-Upgraded | 4530 |  | Sand Creek | Alaska | USA | State Patent or TA |  |  |  | 2014 Existing |  | Station Upgrade |  |  | 7/21/2014 | 2014-07-24 |  | 2014-07-29 |  | Yes
|  | 64.0292 | -142.0758 | K27K | K27K-1 | K27K | Certified Site | 1276 |  | Chicken | Alaska | USA | State Patent or TA |  |  |  | 2014 | Colocated with PBO AC61 | New Install |  |  | 6/14/2014 | 2014-07-07 |  | 2014-08-05 |  | Yes
|  | 64.07 | -139.39 | K28M | K28M-2 | CN.DAWY | Certified Site-Existing | 2688 |  | Dawson City | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 63.8438 | -137.5212 | K29M | K29M-T1 | K29M-T1 | Potential-Reconned Primary Site | 4472 |  | Outside of NWTel Barlow Repeater Site | Yukon | Canada | First Nation |  |  |  | 2016 | VSAT: Horizon SE 2 degrees | New Install |  | 8/17/2014 | [5 empty] | Yes
|  | 61.0926 | -164.2903 | L13K | L13K-1 | L13K-1 | Permit Submitted | 50 |  | Newtok | Alaska | USA | Fish and Wildlife Service |  |  |  | 2017 Descope | FWS-National Refuge System-Yukon Delta | New Install |  | 5/25/2014 | [5 empty] | Yes
|  | 61.3415 | -162.6826 | L14K | L14K-1 | L14K-1 | Permit Submitted | 130 |  | Kuka Creek | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | [5 empty] | Yes
|  | 61.678 | -161.4868 | L15K | L15K-1 | L15K-1 | Permit Submitted | 700 |  | Ungalak Mt. | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 05/23/2014 | [5 empty] | Yes
|  | 61.7099 | -159.4752 | L16K | L16K-1 | L16K-1 | Permit Accepted | 900 |  | Owhat River to East | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 5/23/2014 | [5 empty] | Yes
|  | 62.1343 | -158.2973 | L17K | L17K-3 | L17K-3 | Permit Accepted | 929 |  | Haystack Butte | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 62.2195 | -156.6886 | L18K | L18K-4 | L18K-4 | Permit Submitted | 1040 |  | Granit Mountain | Alaska | USA | BLM |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 62.1816 | -154.8543 | L19K | L19K-1 | L19K | Certified Site | 1450 |  | White Mountain | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 06/19/2015 | 2015-06-20 | 2015-06-22 | 2015-06-30 |  | Yes
|  | 62.4787 | -153.8798 | L20K | L20K-3 | L20K-3 | Certified Site | 2073 |  | St John Hill, Farewell | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install | 6/9/2015 | 06/09/2015 | 08/16/2015 | 2015-08-17 | 2015-08-17 | 2015-08-17 |  | Yes
|  | 62.8968 | -152.187 | L21K | L21K-1 | AK.PPLA | Certified Site-Existing | 4864 |  | Purkeypile | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 12/11/2002 | 2002-12-11 | 2002-12-12 | 2015-02-20 |  | Yes
|  | 62.4058 | -150.2625 | L22K | L22K-1 | AK.CUT | Certified Site-Upgraded | 1883.2 |  | Chulitna | Alaska | USA | State Patent or TA |  |  |  | 2014 Existing | State Select | Station Upgrade |  |  | 4/13/2014 |  |  | 2014-07-29 |  | Yes
|  | 62.8294 | -148.5508 | L23K | L23K-2 | AK.WAT1 | Certified Site-Existing | 2360 |  | Susitna Watana | Alaska | USA | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 63.0753 | -147.376 | L24K | L24K-1 | L24K-1-AK.DHY | Planned Upgrade-Existing | 5293 |  | Denali Highway | Alaska | USA | State Patent or TA |  |  |  | 2016 Existing |  | Station Upgrade | [7 empty] | Yes
|  | 62.9704 | -145.4676 | L25K | L25K-1 | AK.PAX | Certified Site-Upgraded | 3770 |  | Paxson | Alaska | USA | State Selected |  |  |  | 2015 Existing |  | Station Upgrade |  |  |  | 2003-10-06 | 2003-07-20 | 2015-03-20 |  | Yes
|  | 63.0254 | -143.3478 | L26K | L26K-3 | L26K | Certified Site | 2133 |  | Log Cabin Wilderness Lodge | Alaska | USA | Native Patent or IC |  |  |  | 2014 | Mentasta (Village), Private | New Install |  |  | 7/22/2014 | 2014-10-22 |  | 2014-10-31 |  | Yes
|  | 63.0618 | -141.8275 | L27K | L27K-4 | L27K | Certified Site | 2470 |  | Tanana River | Alaska | USA | Military |  |  |  | 2014 | Native Patent or IC | New Install |  |  | 7/24/2014 | 2014-07-25 |  | 2015-04-30 |  | Yes
|  | 63.0845 | -139.99 | L28M | L28M-1 | L28M-1 | Permit Submitted | 4025 |  | White River | Yukon | Canada | Crown Land |  |  |  | 2016 Descope | Crown, BGAN @ 120 degrees | New Install |  | 7/24/2014 | [5 empty] | Yes
|  | 63.1088 | -138.1285 | L29M | L29M-1 | L29M-1 | Permit Submitted | 2900 |  | Grand Valley Creek | Yukon | Canada | Crown Land |  |  |  | 2016 | Crown, BGAN @ 120 degrees | New Install |  | 7/24/2014 | [5 empty] | Yes
|  | 63.3743 | -136.6764 | L30M | L30M-T3 | L30M-T3 | Permit Submitted | 1560 |  | Stewart Crossing | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2016 Descope |  | New Install |  | 8/17/2014 | [5 empty] | Yes
|  | 60.3848 | -166.2009 | M11K | M11K-1 | M11K-1-PB.AB08 | Potential-Existing Other Station | 95 |  | Mekoryuk | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Mekoryuk (Village), FWS-National Refuge System | New Install | [7 empty] | Yes
|  | 60.4132 | -163.3499 | M13K | M13K-1 | M13K-1 | Potential-Reconned Primary Site | 20 |  | Dall Lake | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Bethel (Village), FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | [5 empty] | Yes
|  | 60.7285 | -161.9761 | M14K | M14K-1 | M14K-1 | Potential-Reconned Primary Site | 70 |  | Powerline | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Napakiak (Village), FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | [5 empty] | Yes
|  | 60.86 | -160.7212 | M15K | M15K-1 | M15K-1 | Permit Submitted | 50 |  | Lone clump of spruce | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/25/2014 | [5 empty] | Yes
|  | 61.0223 | -158.9594 | M16K | M16K-2 | M16K-2 | Permit Accepted | 1300 |  | Timber Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 5/25/2014 | [5 empty] | Yes
|  | 61.4009 | -157.4376 | M17K | M17K-2 | M17K-2 | Permit Accepted | 1068 |  | Itulilik Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 61.564 | -156.2282 | M18K | M18K-5 | M18K-5 | Permit Accepted | 380 |  | Stony River Lodge | Alaska | USA | Private-Stony River Lodge |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 61.9037 | -154.3915 | M19K | M19K-1-1 | M19K | Certified Site | 1700 |  | Big River Lodge Airstrip | Alaska | USA | Private |  |  |  | 2015 | Big River Lodge | New Install |  | 9/7/2013 | 06/18/2015 | 2015-06-19 | 2015-06-30 | 2015-06-30 |  | Yes
|  | 61.8802 | -153.1318 | M20K | M20K-3 | M20K | Certified Site | 3626 |  | Styx River | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  | 06/21/2015 | 06/20/2015 | 2015-06-21 | 2015-06-30 | 2015-06-30 |  | Yes
|  | 61.9806 | -151.5292 | M21K | M21K-1 | AK.SKN | Certified Site-Upgraded | 1900 |  | Skwentna | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing |  | Station Upgrade |  |  | 05/15/2006 | 2006-05-15 | 2006-05-16 | 2015-02-20 |  | Yes
|  | 61.7531 | -150.1205 | M22K | M22K-1 | M22K | Certified Site | 187 |  | Willow | Alaska | USA | Private |  |  |  | 2015 | 26631 W. Bryce Cir., Willow, AK, Legal Description: Lot 5A Section 11, T19N, R5W, SM AK. | New Install |  | 4/17/2015 | 5/04/2015 | 2015-05-05 | 2015-05-12 |  |  | Yes
|  | 61.7907 | -147.6756 | M23K | M23K-8-TA.LNHD | LNHD | Recon Target | 2297 |  | Lions Head Mountain | Alaska | USA | State Patent or TA |  |  |  | 2016 |  | New Install | [7 empty] | Yes
|  | 61.832 | -147.329 | M23K | M23K-7-AK.SCM | AK.SCM | Certified Site-Existing | 1050 |  | Sheep Mountain | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | State Microwave Site | Accepted As Is | [5 empty] | 2015-10-26 |  | Yes
|  | 62.5808 | -147.74 | M23K | M23K-6 | AK.WAT6 | Certified Site-Existing | 5510 |  | Susitna Watana | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 61.807 | -148.3318 | M23K | M23K-4 | AK.SAW | Certified Site-Upgraded | 781 |  | Sawmill | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | Native Select, Private | Station Upgrade |  |  | 5/06/2015 | 2015-05-07 |  | 2015-02-20 |  | Yes
|  | 62.1067 | -146.175 | M24K | M24K-3-3 | M24K | Certified Site | 2979 |  | Tolsona, Glenallen | Alaska | USA | State Patent or TA |  |  |  | 2014 |  | New Install |  |  | 7/25/2014 | 2014-08-01 | 2014-08-04 | 2014-08-19 |  | Yes
|  | 62.3987 | -145.1568 | M25K | M25K-1 | HARP | Certified Site | 1906.17 |  | Gakona | Alaska | USA | Existing |  |  |  | 2015 | UAF Lease | Station Upgrade |  |  | 4/21/2015 | 2015-04-22 | 2015-04-22 | 2015-04-29 |  | Yes
|  | 62.4013 | -142.9962 | M26K | M26K_ME | M26K | Certified Site | 2920 |  | Devil's Mountian Lodge, Nebesna | Alaska | USA | Private |  |  |  | 2015 | Devil's Mountain Lodge | New Install |  |  | 07/12/2015 | 2015-07-13 | 2015-07-13 | 2015-07-16 |  | Yes
|  | 62.3579 | -141.878 | M27K | M27K-5 | M27K | Certified Site | 5050 |  | Edge Creek | Alaska | USA | National Park Service |  |  |  | 2015 | NPS-Wrangell-St Elias | New Install |  |  | 07/10/2015 | 2015-07-12 | 2015-07-13 | 2015-07-16 |  | Yes
|  | 62.4141 | -140.8606 | M28M | M28M-2 | CN.BVCY | Certified Site-Existing | 2237 |  | Beaver Creek Airport | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 62.4415 | -138.4612 | M29M | M29M-1 | M29M-1 | Permit Submitted | 4320 |  | Somme Creek | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2016 | Crown, BGAN @ 120 degrees | New Install |  | 7/24/2014 | [5 empty] | Yes
|  | 62.5763 | -136.7935 | M30M | M30M-T2 | M30M | Certified Site | 2564 |  | Minto | Yukon | Canada | First Nation |  |  |  | 2015 | Selkirk FN | New Install |  | 05/26/2015 | 10/18/2015 | 2015-10-18 | 2015-10-17 | 2015-10-18 |  | Yes
|  | 62.2024 | -134.3906 | M31M | M31M-T3 | M31M | Certified Site | 2096 |  | Drury Creek Highway Camp | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2015 |  | New Install |  | 8/4/2014 | 10/17/2015 | 2015-10-17 | 2015-12-03 | 2015-12-03 |  | Yes
|  | 59.9237 | -161.685 | N14K | N14K-1 | N14K-1 | Permit Submitted | 43 |  |  | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/28/2014 | [5 empty] | Yes
|  | 60.1686 | -160.0919 | N15K | N15K-1 | N15K-1 | Permit Submitted | 1455 |  | Lake Creek | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/28/2014 | [5 empty] | Yes
|  | 60.4742 | -158.7689 | N16K | N16K-1 | N16K-1 | Permit Accepted | 1890 |  | Nishlik Lake | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 5/28/2014 | [5 empty] | Yes
|  | 60.5268 | -157.1867 | N17K | N17K-3.5 | N17K-3.5 | Permit Accepted | 1059 |  | Finn Mountain | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 60.6801 | -155.8897 | N18K | N18K-3-1 | N18K | Certified Site | 1877 |  | Killae Creek | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 6/13/2015 | 2015-06-13 | 2015-06-14 | 2015-06-16 |  | Yes
|  | 60.8132 | -154.4838 | N19K | N19K-6 | N19K | Certified Site | 3753 |  | Bonanza | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 6/12/2015 | 2015-06-13 |  | 2015-06-16 |  | Yes
|  | 61.2002 | -152.2089 | N20K | N20K-1 | AV.SPCR | Equipment Installed | 3228 |  | Ckakachatna River, Mt Spurr | Alaska | USA | State Patent or TA |  |  |  | 2015 | AVO site | Station Upgrade |  |  | 08/13/2015 | 2015-08-14 | 2005-02-11 |  |  | Yes
|  | 61.464 | -150.7444 | N21K | N21K-1 | AK.SSN | Certified Site-Upgraded | 4297 |  | Mount Susitna | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | Private | Station Upgrade |  |  | 08/05/2015 | 2008-08-15 | 2008-08-16 | 2015-02-20 |  | Yes
|  | 61.0889 | -149.739 | N22K | N22K-3 | AK.RC01 | Certified Site-Upgraded | 1281 |  | Knik | Alaska | USA | Military |  |  |  | 2014 Existing | State Patent or TA, State Select, Native Select, Private |  |  |  |  | 2014-08-28 | 2014-08-28 | 2014-09-04 |  | Yes
|  | 61.592 | -149.131 | N22K | N22K-4 | AT.PMR | Certified Site-Existing | 100 |  | Palmer | Alaska | USA | Private |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 61.4131 | -148.4585 | N23K | N23K-1 | AK.KNK | Certified Site-Upgraded | 1978 |  | Chickaloon | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing |  | Station Upgrade |  |  | 5/11/2015 | 2015-05-12 | 2010-06-14 | 2015-02-20 |  | Yes
|  | 61.493 | -145.9206 | N24K | N24K-1 | AK.KLU | Certified Site-Existing | 3784 |  | Klutina Pass | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | State Select | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 61.6061 | -144.5982 | N25K | N25K-3 | N25K | Certified Site | 3566 |  | Chitina, Valdez-Cordova | Alaska | USA | State Patent or TA |  |  |  | 2014 |  | New Install |  |  | 9/30/2014 | 2014-10-01 | 2014-10-02 | 2014-10-07 |  | Yes
|  | 61.3841 | -143.0219 | N26K | N26K-1 | AK.MCAR | Certified Site-Upgraded | 1476 |  | McCarthy | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | WDL-National Park Service | Station Upgrade |  |  | 07/27/2015 | 2015-07-28 | 2013-01-02 | 2015-02-20 |  | Yes
|  | 61.7579 | -141.7048 | N27K | N27K-2 | N27K-2 | Permit Accepted | 3648 |  | Solo Creek | Alaska | USA | National Park Service |  |  |  | 2015 Descope | NPS-Wrangell-St Elias, State Select, Private, Airstrip, BGAN Good Signal @ 120 degrees | New Install | [7 empty] | Yes
|  | 61.7755 | -140.4595 | N28M | N28M-2 | CN.YUK3 | Certified Site-Existing | 6839 |  | Moose Peak | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 61.4348 | -138.5463 | N29M | N29M-2 | CN.YUK4 | Certified Site-Existing | 6549 |  | Kluane Lake | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 61.4594 | -137.0875 | N30M | N30M-T3 | N30M-T3 | Permit Submitted | 948 |  | Aishihik | Yukon | Canada | Crown Land |  |  |  | 2016 |  | New Install |  | 05/24/2015 | [5 empty] | Yes
|  | 61.4817 | -135.7796 | N31M | N31M-T2 | N31M | Certified Site | 2349 |  | Braeburn Lodge | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2015 |  | New Install |  | 8/4/2014 | 10/14/2015 | 2015-10-14 | 2015-10-20 | 2015-10-14 |  | Yes
|  | 61.1511 | -133.0819 | N32M | N32M-T1 | N32M-T1 | Permit Submitted | 2634 |  | Quiet Lake Highway | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2016 | VSAT: Horizon-Trees at 14 degrees; Hills at 8 degrees | New Install |  | 8/26/2014 | [5 empty] | Yes
|  | 57.1776 | -170.2455 | O08K | O08K-1 | AK.SPIA | Certified Site-Upgraded | 276 |  | St. Paul Island | Alaska | USA | Native Patent or IC |  |  |  | 2015 Existing | St. Paul (Village), FWS-National Refuge System | Station Upgrade | [5 empty] | 2015-02-20 |  | Yes
|  | 59.2533 | -161.2638 | O14K | O14K-1 | O14K-1 | Permit Submitted | 450 |  | Tigyukauivet Mt. | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/28/2014 | [5 empty] | Yes
|  | 59.1681 | -159.6727 | O15K | O15K-2 | O15K-2 | Permit Submitted | 240 |  | Kulukak River | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Togiak | New Install |  | 5/28/2014 | [5 empty] | Yes
|  | 59.5938 | -158.0927 | O16K | O16K-1 | O16K-1 | Potential-Reconned Primary Site | 647 |  | Kenakuchuk Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  | 5/26/2014 | [5 empty] | Yes
|  | 59.7733 | -157.0947 | O17K | O17K-1 | O17K-1 | Permit Accepted | 540 |  | Koliganek | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install | [7 empty] | Yes
|  | 59.8542 | -155.208 | O18K | O18K-JM | O18K | Certified Site | 1775 |  | Koktuh Hill | Alaska | USA | State of Alaska |  |  |  | 2015 | DNR | New Install |  | 4/2/2015 | 06/14/2015 | 2015-06-14 | 2015-06-16 | 2015-06-30 |  | Yes
|  | 60.1952 | -154.3201 | O19K | O19K-2 | O19K | Certified Site | 315 |  | Port Alsworth | Alaska | USA | NPS |  |  |  | 2015 | Lake Clark | New Install |  | 4/2/2015 | 6/09/2015 | 2015-06-09 |  | 2015-06-16 |  | Yes
|  | 60.0815 | -152.624 | O20K | O20K-1 | PB.AC47 | Certified Site | 922 |  | Slope Mountain | Alaska | USA | NPS |  |  |  | 2015 | FWS-National Refuge System | New Install |  |  | 06/23/2015 | 2015-06-24 | 2015-06-30 | 2015-06-30 |  | Yes
|  | 60.7683 | -151.1539 | O21K | O21K-1 | AK.CAPN | Certified Site-Upgraded | 164 |  | Soldotna | Alaska | USA | State Patent or TA |  |  |  | 2014 Existing | State Select, Private | Station Upgrade |  |  | 5/14/2014 | 2014-06-02 |  | 2014-07-29 |  | Yes
|  | 60.4814 | -149.7241 | O22K | O22K-1 | O22K | Certified Site | 459 |  | Moose Pass | Alaska | USA | State Patent or TA |  |  |  | 2014 | Forest Service | New Install |  |  | 5/17/2014 | 2014-05-30 | 2014-06-02 | 2014-06-18 |  | Yes
|  | 60.8584 | -148.3334 | O23K | O23K-1-AK.PWL | AK.PWL | Certified Site-Existing | 1804 |  | Port Wells | Alaska | USA | Forest Service |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-10-26 |  | Yes
|  | 60.88 | -147.1 | O23K | O23K-2 | AK.GLI | Certified Site-Existing | 498 |  | Glacier Island | Alaska | USA | Forest Service |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 60.5493 | -145.7479 | O24K | O24K-1 | AK.EYAK | Certified Site-Existing | 453 |  | Cordova Ski Area | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | Forest Service, Private | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 60.9682 | -144.603 | O25K | O25K-1 | AK.BMR | Certified Site-Existing | 2679 |  | Bremner River | Alaska | USA | National Park Service |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 60.75 | -143.09 | O26K | O26K-1 | AK.CRQ | Certified Site-Existing | 3743 |  | Cirque | Alaska | USA | National Park Service |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 60.97 | -141.34 | O27K | O27K-1 | AK.CTG | Certified Site-Existing | 3743 |  | Chitna Glacier | Alaska | USA | National Park Service |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 60.7721 | -140.1919 | O28M | O28M-T1 | O28M-T1 | Permit Submitted | 8502 |  | Mt Upton, Kluane Nation Park Reserve | Yukon | Canada | Parks Canada |  |  |  | 2016 | VSAT: Horizon SE 7 degrees | New Install |  | 8/1/2014 | [5 empty] | Yes
|  | 60.9432 | -138.3626 | O29M | O29M-4 | CN.YUK6 | Certified Site-Existing | 6939 |  | Outpost Mtn | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 60.3024 | -138.5754 | O29M | O29M-T3 | O29M-T3 | Permit Submitted | 4687 |  | Confluence of Dusty & Lowell Glacier | Yukon | Canada | Parks Canada |  |  |  | 2016 | VSAT: Horizon SE = 7 degrees | New Install | [7 empty] | Yes
|  | 60.83 | -137.5 | O30M | O30M-2 | CN.HYT | Certified Site-Existing | 32.51 |  | Pine Lake | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 60.7704 | -136.0906 | O30N | O30N-T1 | O30N-T1 | Permit Submitted | 2719 |  | Mendenhall River NWTel Site | Yukon | Canada | Crown Land |  |  |  | 2016 |  | New Install | 09/24/2015 | 09/24/2015 | [5 empty] | Yes
|  | 60.66 | -134.88 | O31M | O31M-1 | CN.WHY | Certified Site-Existing | 3100 |  | Grey Mountain | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 56.5786 | -169.6614 | P08K | P08K | P08K | Initial Site | 20 |  | St George Island | Alaska | USA | Native Patent or IC |  |  |  | 2017 | St. George (Village), FWS-National Refuge System | New Install | [7 empty] | Yes
|  | 59.0314 | -157.9902 | P16K | P16K-1 | P16K-1 | Permit Accepted | 312 |  | Nushgak River | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 5/29/2014 | [5 empty] | Yes
|  | 59.1951 | -156.4386 | P17K | P17K-4-1 | P17K-4-1 | Permit Submitted | 249 |  | Kvichak River | Alaska | USA | State Patent or TA |  |  |  | 2017 | North Shore Borough | New Install | [7 empty] | Yes
|  | 59.3922 | -155.2292 | P18K | P18K-1 | P18K | Certified Site | 2038 |  | Big Mountain | Alaska | USA | Military |  |  |  | 2015 | State Patent or TA | New Install |  |  | 6/15/2015 | 2015-06-16 | 2015-10-11 | 2015-10-11 |  | Yes
|  | 59.65 | -153.23 | P19K | P19K-1 | AV.OPT | Certified Site | 273 |  | Oil Point | Alaska | USA | Native Patent or IC |  |  |  | 2015 |  | New Install |  |  | 06/24/2015 | 2015-06-25 | 2015-06-24 | 2015-06-30 |  | Yes
|  | 59.6578 | -151.6494 | P20K | P20K-1 | AK.HOM | Certified Site-Upgraded | 721 |  | Anchor Point | Alaska | USA | State Patent or TA |  |  |  | 2014 Existing | State Select, Private |  |  |  | 11/11/2013 | 2014-08-10 |  | 2014-08-22 |  | Yes
|  | 59.7417 | -150.7414 | P21K | P21K-6 | AK.BRSE | Certified Site-Existing | 1770 |  | Bradley Lake South | Alaska | USA | Existing |  |  |  | 2015 Existing | UAF site | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 60.1049 | -149.4507 | P22K | P22K-1 | AK.SWD | Certified Site-Existing | 262 |  | Seward | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | State Select, Private | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 59.9979 | -147.403 | P23K | P23K-1 | P23K-1-PB.AC79 | Potential-Existing Other Station | 804 |  | Montague Island | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Forest Service | New Install | [7 empty] | Yes
|  | 59.9273 | -144.417 | P25K | P25K-1 | AK.KAI | Planned Upgrade-Existing | 997 |  | Kayak Island | Alaska | USA | Forest Service |  |  |  | 2016 Existing | FWS-National Refuge System | Station Upgrade | [7 empty] | Yes
|  | 60.121 | -143.2821 | P26K | P26K-1 | AK.BGLC | Certified Site-Existing | 49 |  | Bering Glacier BLM Camp | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | FWS-National Refuge System | Accepted As Is | [7 empty] | Yes
|  | 60.17 | -141.9485 | P27K | P27K-1 | AK.MESA | Certified Site-Existing | 6418 |  | Mesa | Alaska | USA | National Park Service |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 59.6659 | -139.4036 | P28K | P28K-2 | AK.PNL | Certified Site-Existing | 1800 |  | Yukatat Peninsula | Alaska | USA | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-10-26 |  | Yes
|  | 60.0967 | -140.2566 | P28K | P28K-1 | P28K-1-AK.PIN | Planned Upgrade-Existing | 2696 |  | Pinnacle | Alaska | USA | National Park Service |  |  |  | 2016 Existing |  | Station Upgrade | [7 empty] | Yes
|  | 59.6303 | -137.7378 | P29M | P29M-T1 | P29M-T1 | Potential-Reconned Primary Site | 2251 |  | Windy Craggy Mine Site | British Columbia | Canada | BC Parks-Tatsenshini-Alsek Prov. Park |  |  |  | 2016 | VSAT: Horizon SE 3 degrees | New Install |  | 7/22/2014 | [5 empty] | Yes
|  | 60.1221 | -136.9574 | P30M | P30M-T1 | P30M-T1 | Permit Submitted | 3005 |  | MDFC GPS Site | Yukon | Canada | Crown Land |  |  |  | 2016 | VSAT: Horizon SE 12 degrees | New Install |  | 5/31/2014 | [5 empty] | Yes
|  | 60.2033 | -135.1367 | P31M | P31M-4 | P31M-4 | Permit Submitted | 3555 |  | Carcross | Yukon | Canada | Crown Land |  |  |  | 2016 |  | New Install | [7 empty] | Yes
|  | 59.5898 | -133.7146 | P32M | P32M-T1 | P32M-T1 | Permit Submitted | 2606 |  | Atlin | British Columbia | Canada | CBC Lease-Area of Lease TBC |  |  |  | 2016 |  | New Install |  | 7/19/2014 | [5 empty] | Yes
|  | 60.2114 | -132.8174 | P33M | P33M-T3 | P33M | Certified Site | 3496 |  | Teslin | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2015 |  | New Install |  | 05/02/2015 | 10/15/2015 | 2015-10-15 | 2015-10-15 | 2015-10-15 |  | Yes
|  | 58.6816 | -156.6527 | Q16K | Q16K | Q16K | Initial Site | 91 |  | King Salmon | Alaska | USA | National Park Service | Native Patent | Fish and Wildlife Service | Private | 2016 | Site is planned to be co-located with an existing PBO GPS station with same coordinates. | New Install | [7 empty] | Yes
|  | 58.26 | -155.89 | Q17K | Q17K-2 | Q17K-2-AV.CNTC | Potential-Existing Seismic Station | 3600 |  | Contact Creek | Alaska | USA | National Park Service |  |  |  | 2016 | NPS-Wilderness Desig | New Install | [7 empty] | Yes
|  | 58.6483 | -155.0081 | Q18K | Q18K-3 | Q18K-3-AV.KAHC | Potential-Existing Seismic Station | 1250 |  | Lake Grosvenor | Alaska | USA | National Park Service |  |  |  | 2016 | WDL-NPS-Wilderness Desig | New Install | [7 empty] | Yes
|  | 58.9287 | -153.6446 | Q19K | Q19K-1 | PB.AC06 | Certified Site | 1950 |  | Cape Douglas | Alaska | USA | National Park Service |  |  |  | 2015 |  | New Install |  |  | 08/14/2015 | 2015-08-15 | 2015-08-16 | 2015-08-15 |  | Yes
|  | 58.6097 | -152.394 | Q20K | Q20K | Q20K-PB.AC39 | Potential-Existing Other Station | 152.652 |  | Shuayk Island | Alaska | USA | Existing |  |  |  | 2016 |  | New Install | [7 empty] | Yes
|  | 59.4296 | -146.3499 | Q23K | Q23K-1 | Q23K | Certified Site | 151 |  | Middleton Island | Alaska | USA | Native Patent or IC |  |  |  | 2014 | FWS | New Install |  |  | 8/15/2014 | 2014-08-17 | 2014-08-19 | 2014-08-16 |  | Yes
|  | 59.0912 | -138.2136 | Q29K | Q29K-2 | AK.DCPH | Certified Site-Existing | 2198 |  | Deception Hills | Alaska | USA | National Park Service |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 59.455 | -136.3659 | Q30M | Q30M-1 | CN.PLBC | Potential-Existing Seismic Station | 1984 |  | Pleasant Camp | British Columbia | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is | [7 empty] | Yes
|  | 59.4601 | -135.329 | Q31K | Q31K-1 | Q31K-1-AT.SKAG | Certified Site-Existing | 426 |  | Tulsequah | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | State Select, Private | Accepted As Is | [5 empty] | 2015-02-20 |  | Yes
|  | 58.9601 | -132.2692 | Q32M | Q32M-T2 | Q32M-T2 | Permit Submitted | 6394 |  | Nakina River | British Columbia | Canada | Crown BC |  |  |  | 2016 | VSAT: Horizon SE 2 degrees | New Install |  | 7/21/2014 | [5 empty] | Yes
|  | 57.5672 | -157.5742 | R16K | R16K-1 | R16K-1-PB.AC52 | Potential-Existing Other Station | 117 |  | Ugashik | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Private | New Install | [7 empty] | Yes
|  | 57.6398 | -156.3871 | R17K | R17K-2 | R17K-2 | Permit Submitted | 955 |  | Ugashik Creek | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-Becharof, Native Patent or IC | New Install |  | 5/29/2014 | [5 empty] | Yes
|  | 57.5665 | -154.4524 | R18K | R18K-1 | R18K-1 | Potential-Reconned Primary Site | 140 |  | Karluk | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Karlu Village, Private | New Install |  | 8/29/2014 | [5 empty] | Yes
|  | 57.7828 | -152.5835 | R19K | R19K-3 | II.KDAK | Certified Site-Existing | 141 |  |  | Alaska | USA | BLM |  |  |  | 2015 Existing |  | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 58.4136 | -135.7393 | R31K | R31K-1 | R31K-1 | Permit Accepted | 30 |  | Gustavus City Hall | Alaska | USA | State Patent or TA | Private |  |  | 2016 | Private | New Install |  | 9/18/2014 | [5 empty] | Yes
|  | 58.4168 | -134.5453 | R32K | R32K-1 | R32K-1-PB.AB50 | Potential-Existing Other Station | 112 |  | Juneau | Alaska | USA | Forest Service |  |  |  | 2016 |  | New Install | [7 empty] | Yes
|  | 59.3952 | -130.9675 | R33M | R33M-T1 | R33M-T1 | Permit Submitted | 4709 |  | Jennings River | British Columbia | Canada | Crown BC |  |  |  | 2016 | VSAT: Horizon SE 1 degree | New Install |  | 7/20/2014 | [5 empty] | Yes
|  | 55.7038 | -162.0651 | S12K | S12K-1 | S12K-1-AV.BLHA | Potential-Existing Seismic Station | 1038 |  | Black Hill | Alaska | USA | State Patent or TA |  |  |  | 2016 |  | New Install | [7 empty] | Yes
|  | 55.3491 | -160.4766 | S13K | S13K-1 | S13K-1-AT.SDPT | Planned Upgrade-Existing | 230 |  | Sand Point | Alaska | USA | Native Patent or IC |  |  |  | 2016 Existing | FWS-National Refuge System | Station Upgrade | [7 empty] | Yes
|  | 56.28 | -159.555 | S14K | S14K-1 | S14K-1-AV.VNFG | Potential-Existing Seismic Station | 3268 |  | Mount Veniaminof, Fog Glacier | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System | New Install | [7 empty] | Yes
|  | 56.3014 | -158.4142 | S15K | S15K-2 | S15K-2-AT.CHGN | Planned Upgrade-Existing | 433 |  | Chignik | Alaska | USA | Native Patent or IC |  |  |  | 2016 Existing | Chignik (Village), FWS-National Refuge System, Private | Station Upgrade | [7 empty] | Yes
|  | 56.56 | -154.1819 | S18K | S18K-2 | AK.SII | Certified Site-Existing | 492 |  | Sitkinak Island Coast Guard | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | FWS-National Refuge System | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 57.2225 | -153.2875 | S19K | S19K-3 | S19K-3-AT.OHAK | Planned Upgrade-Existing | 120 |  | Old Harbor | Alaska | USA | Native Patent or IC |  |  |  | 2016 Existing | Old Harbor (Village), FWS-National Refuge System | Station Upgrade | [7 empty] | Yes
|  | 57.9551 | -136.2182 | S31K | S31K-1 | S31K-1 | Permit Accepted | 20 |  | Pelican | Alaska | USA | State Patent or TA | Private |  |  | 2016 | Forest Service, Private, Internet at building with dish on property | New Install |  | 9/18/2014 | [5 empty] | Yes
|  | 57.4688 | -134.5765 | S32K | S32K-2 | S32K-2 | Potential-Reconned Primary Site | 70 |  | Killisnoo Island | Alaska | USA | Forest Service |  |  |  | 2016 Descope | Private | New Install |  | 9/14/2014 | [5 empty] | Yes
|  | 57.5967 | -133.3558 | S33K | S33K-1 | S33K-1 | Permit Submitted | 80 |  | Windham Bay | Alaska | USA | Private |  |  |  | 2016 | Private | New Install |  | 9/14/2014 | [5 empty] | Yes
|  | 57.9127 | -131.1311 | S34M | S34M-T1 | S34M-T1 | Potential-Reconned Primary Site | 964 |  | Telegraph Creek | British Columbia | Canada | LDM Highway Yard Telegraph Creek |  |  |  | 2016 | DSL, Alternate VSAT: Horizon SE 10 degrees | New Install |  | 8/28/2014 | [5 empty] | Yes
|  | 53.8465 | -166.502 | T09K | T09K-2 | AK.UNV | Certified Site-Upgraded | 230 |  | Unalaska | Alaska | USA | Native Patent or IC |  |  |  | 2015 Existing | FWS-National Refuge System, Private | Station Upgrade | [5 empty] | 2015-02-20 |  | Yes
|  | 54.8573 | -163.4155 | T10K | T10K-2 | AK.FALS | Certified Site-Existing | 51 |  | False Pass | Alaska | USA | Native Patent or IC |  |  |  | 2015 Existing | False Pass (Village), FWS-National Refuge System | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 55.8225 | -155.621 | T17K | T17K-2 | AK.CHI | Certified Site-Existing | 656 |  | Chirikof Island | Alaska | USA | FWS |  |  |  | 2015 Existing | WDL-FWS-National Refuge System | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 57.06 | -135.32 | T32K | T32K-1 | AT.SIT | Certified Site-Existing | 169 |  | Sitka | Alaska | USA | State Patent or TA |  |  |  | 2015 Existing | Forest Service, National Park Service, Private | Accepted As Is | [5 empty] | 2015-02-02 |  | Yes
|  | 56.8219 | -132.9136 | T33K | T33K-1 | T33K-1-PB.AB51 | Potential-Existing Other Station | 349 |  | Kupreanof | Alaska | USA | State Patent or TA |  |  |  | 2016 |  | New Install | [7 empty] | Yes
|  | 56.4191 | -132.3466 | T34K | T34K-2 | US.WRAK | Certified Site-Existing | 275 |  | Wrangell Island | Alaska | USA | Native Patent or IC |  |  |  | 2015 Existing | State Patent or TA, Forest Service. Global Seismic Network Station. | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 56.9811 | -130.2493 | T35M | T35M-T2 | T35M-T2 | Potential-Reconned Primary Site | 2020 |  | Bob Quinn LDM Yard | British Columbia | Canada | Lake District Maintenance |  |  |  | 2016 | VSAT: Horizon SE 13 degrees, XPlorNet ISP in use by LDM on site | New Install |  | 8/29/2014 | [5 empty] | Yes
|  | 52.9732 | -168.853 | U06K | U06K-3 | AK.NIKH | Certified Site-Existing | 656 |  | Nikolski High Hill | Alaska | USA | Military |  |  |  | 2015 Existing | MIL-Dept of Air Force, FWS-National Refuge System, Native Patent or IC, Nikolski (Village) | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 54.831 | -159.5895 | U13K | U13K-1 | AK.CHN | Certified Site-Existing | 275 |  | Unga | Alaska | USA | FWS |  |  |  | 2015 Existing | FWS-National Refuge System | Accepted As Is | [5 empty] | 2015-04-30 |  | Yes
|  | 56.1144 | -133.1213 | U33K | U33K-1 | U33K-1 | Permit Submitted | 31 |  | Whale Pass | Alaska | USA | State Patent or TA | Private |  |  | 2016 | State Patent or TA, Forest Service | New Install |  | 9/17/2014 | [5 empty] | Yes
|  | 55.9169 | -131.7983 | U34K | U34K-1 | U34K-1 | Permit Submitted | 90 |  | Yes Bay | Alaska | USA | Forest Service |  |  |  | 2016 | Private | New Install |  | 9/16/2014 | [5 empty] | Yes
|  | 55.9155 | -130.0257 | U35K | U35K-2 | U35K-2 | Permit Accepted | 90 |  | Hyder Community Center | Alaska | USA | State Patent or TA | Private |  |  | 2016 | Forest Service, Private | New Install |  | 9/16/2014 | [5 empty] | Yes
|  | 55.47 | -133.12 | V34K | V34K-4 | AT.CRAG | Certified Site-Existing | 25 |  | Craig | Alaska | USA | Native Patent or IC |  |  |  | 2015 Existing | Craig (Village of), Forest Service | Accepted As Is | [5 empty] | 2015-02-02 |  | Yes
|  | 55.3281 | -131.6147 | V35K | V35K-1 | V35K-1 | Permit Submitted | 180 |  | Ketchikan | Alaska | USA | State Patent or TA |  |  |  | 2016 | Private | New Install |  | 9/16/2014 | [5 empty] | Yes